# The quality of the local environment will improve through keeping Camelon and Tamfourhill: Tidy, Clean & Green.

Key Activities	Lead	Key Partners	Method & Process	Timescales	Key Indicators
Support Litter Picks & community Clean ups	JRH	KSB, TCV, CJFC, Primary & Secondary schools, Early Years Centres, TCH, TTRO, Friends of Nailer Park, FVSC, Woodcraft Folk, Cyrenians, Recovery Community, SACRO, Transform FV, FC Waste Services, Scottish Canals, Go forth and Clyde, Canal College, Local Volunteers, Local businesses	Coordinate and support clear ups from TCH / Data to be recorded for each litter pick / Target agreed hot spots / lease with FC Waste Services / Apply FC guidelines, procedures & protocols / Link community clear ups with conservation and outdoor learning opportunities. / Target clear ups on the canal, towpath, and environs / Ensure Synergy with FC littering strategy	Nov 2020 – ongoing	Monthly litter picks & community clear ups implemented. / 50% Reduction of local litter & fly-tipping at agreed target locations / Involve up to 10 local volunteers every month. / Support at least 1 community group or org. every 2 months. / Contribute to at least 2 Accreditation opportunities for young volunteers per year / Collate data for KSB surveys Quarterly.
Promote positive Behaviour Change. / Facilitate community Education opportunities& volunteering	JRH	Primary & Secondary Schools, TCV, CLD, TCH, CCH, CJFC, KSB, Local Youth groups, FC Waste Services/ Cleansing Housing/community engagement, FVSC, local shops, Scottish Canals, and businesses. / Local Schools, CLD, TCV, SACRO, Recovery Community, Transform Forth Valley, local youth groups, FC Waste Services, Scottish Canals, Go Forth & Clyde, Canal College, KSB, Local Volunteers	Promote a variety of nudge interventions. / Social Media and Press updates / Produce publicity & promotional materials / Set up a Clean-up pledge to sign / Develop information resources for tenants / Develop and deliver workshops & environmental activities. / Ensure Synergy with FC littering strategy. / Encourage Outdoor learning, educational inputs, and conservation projects. / Target signage and messaging at priority locations. / Sustain volunteering opportunities for disadvantaged groups and individuals. / Ensure involvement of local people impacted by the criminal justice system and substance dependency.	Jan 2021 - ongoing	Establish a young community safety volunteers forum meeting monthly / Produce and distribute posters, flyers, and signage in neighbourhoods. / Introduce 20 new sponsored bins and other messaging templates / Produce a tenant’s information resource. / Deliver participative workshops & nudge activities quarterly. / Support one group per annum to gain a recognised award, training qualification or recognised accreditation. / Monthly volunteering sessions implemented involving disadvantaged groups and members of the recovery community.
Greening & Growing	DR	FC Growing, FC Housing, Local Residents, Falkirk Food Consortium, TTRO, Friends of Nailer Park, Primary schools, Early Learning Centres, Forth Valley Sensory Centre, Local Community Hubs/Centre, Love Falkirk, TCV, Cyrenians, Forth Environment Link, Police, CLD	Identify and confirm suitable locations and consult with local tenants/residents / Establish and support a Group of local community growing volunteers / Secure resources to develop and sustain target areas	Sept 2020- Dec 2021	Established 2 community growing sites. / 2 Community allotment sites established with up to 8 plots. / Establish 4 wildflower/pop up parks. / Community Growing Development Group meeting monthly. / 10 volunteers regularly involved with Greening & Growing activities. / Local Schools actively engaged in community growing activity
Targeted support & interventions.	JRH	Community Festivals, Events, Mariners Day, Camelon Arts, Community Sports Hub.	Support specific campaigns/events as appropriate / Coordinate Targeted litter picks / Engage & consult community on matters of specific concern	Oct 2020- March 2022	Reinstatement of fortnightly green bin collection / Engage Tenants re. recycling / Targeted litter picks & environmental activities delivered at community events and gala/fun days.