## Table_A_Discounted_total_fund
Category of total discounted cost by funding source	£m
LUF Funding	£20,239,198
Other Public Sector Funding	£34,673,794
Private Sector Funding	£0.00
Total	£54,912,993

Assumptions
example - price base year
Including OB and inflation
Price base year 2021

## Table_B_Discounted_Benefit
Catergory of benefit	£m
Direct Land Value Uplift	£64,200,468
Indirect Land Value Uplift	£30,647,938
Labour Supply Impacts	£781,306
Active Travel Impacts	£2,282,095
Distributional Impacts	£1,362,778

Total	£99,274,585

Assumptions
example - price base year

Price base year 2021

## Table_C_Funding_Profile
Funding Sources	2021-22	2022-23	2023-24	2024-25	Total
UKG Funding Sought	£3,789,839	£10,228,086	£5,982,075	£0	£20,000,000
Local Authority Contribution	£6,492,752	£17,522,758	£10,248,490	£0	£34,264,000
Third Party Contribution	£0	£0	£0	£0	£0
Total	£10,282,591	£27,750,844	£16,230,565	£0	£54,264,000

Assumptions

Please not this is note discounted and does not include OB.

## Table_D_Costing_estimates
Cost heading	Costs (£)	Date Estimated	Status
Site Clearance	£389,809.38	20 November 2020	Design Team pre-tender cost estimates.
Fencing	£101,497.46
Road Restraint Systems	£787,741.55
Drainage	£1,595,976.81
Earthworks	£3,716,998.63
Pavements	£4,328,391.66
Kerbs, Footways & Paved Areas	£1,694,127.49
Traffic Signs & Road Markings	£583,604.29
Road Lighting Columns, Brackets & CCTV Masts	£653,206.04
Electrical Work for Road Lighting & Traffic Signs	£669,999.84
Motorways Communications & Technology	£0.00
Piling & Embedded Retaining Walls	£4,251,666.07
Structural Concrete	£877,093.90
Steelwork for Structures	£4,746,596.31
Protection of Steelwork against Corrosion	£470,628.00
Waterproofing for Structures	£259,128.20
Bridge Bearings	£68,000.00
Bridge Expansion Joints & Sealing of Gaps	£0.00
Brickwork, Blockwork & Stonework	£0.00
Special Structures (Midthorn Culvert)	£150,976.50
Accommodation Works & Works for Statutory Undertakers	£2,092,338.20
Landscape & Ecology	£723,678.02
Maintenance Painting of Steelwork	£0.00
Preliminaries	£4,928,255.21
Contractors Fee/Overheads and Profit	£2,587,333.98
Inception / Planning Fee	£1,248,418.00
Project / Design Team Fees (Estimate)	£1,408,072.92
Project Management Team Fees (Estimate)	£1,854,256.02
G.I. 2019	£520,000.00
Risk [per @Risk Output Report P85]	£5,736,780.00
Historic Design and Preperation Costs	£5,822,308.82
Inflation	£1,997,116.70
	£54,264,000.00

## Table_E_Delivery_Milestones
	Dates
Works Activity	Start	Finish	Completion of works (if different)
Planning	Mar-21	Oct-21
Stage 3 Detailed Design	Mar-21	Sep-21
Highways: Peer Review	Mar-21	Apr-21
Highways: Traffic Modelling	Mar-21	Apr-21
Highways: Incorporate Planning Outcomes	May-21	Jun-21
Structure: Geotech	Mar-21	Apr-21
Structure: Architechtural/Electrical	Mar-21	May-21
Structure: Structures	Mar-21	Sep-21
Approvals: Falkirk Council	Aug-21	Aug-21
Approvals: Petroineos	May-21	Jun-21
Tender Documentation	Apr-21	Jun-21
Pre-construction: summary	Mar-21	Nov-21
Pre-construction: enabling works	Jul-21	Mar-22
Pre-construction: Delivery Agreement	Jun-21	Nov-21
Construction	Nov-21	Jan-25
Licences/Permits: CAR license for proposed scheme	Mar-21	Mar-21
Licences/Permits: construction site licence	Mar-21	Mar-21
Licences/Permits: exemption from waste management licence	Mar-21	Mar-21
Q&E Plan: Quality Plan	Nov-21	Feb-22
Q&E Plan: Environmental plan	Nov-21	Feb-22
3rd party interface/permits: temporary traffic restriction order	Nov-21	Feb-22
3rd party interface/permits: road opening permit	Nov-21	Feb-22
Construction phase plan	Nov-21	Jan-22
Construction	Feb-22	Jul-24
Handback	Dec-23	Jul-24

## Table_F_Bid_Monitoring_and_Eval
Measure	Data To be used	Baseline data source	Data collection methods	Frequency of data collection	Benefit owner (if Applicable)
	Inputs
Falkirk Council Co-Funding	£31,864,000	Falkirk LUF Bid Submission	Project management records as per Section 6.3 Management and 6.4 M&E	Monthly	Falkirk Council
LCTT Co-Funding	£2,400,000	Falkirk LUF Bid Submission	Project management records as per Section 6.3 Management and 6.4 M&E	Monthly	Falkirk Council
LUF Investment	£20,000,000	Falkirk LUF Bid Submission	Project management records as per Section 6.3 Management and 6.4 M&E	Monthly	Falkirk Council
	Outputs
Dual carriageway upgrading : to the A904, from M9 Junction 6 (Earlsgate) to Forth Valley College; and to the A9 from the Etna Road (Helix Park) roundabout to the Falkirk Stadium roundabout		WSP Deisgn Package	Project management records as per Section 6.3 Management and 6.4 M&E	Upon Completion	Falkirk Council
Three new roundabouts at Middlefield Road, West Mains Road and serving the proposed Falkirk Gateway development site		WSP Deisgn Package	Project management records as per Section 6.3 Management and 6.4 M&E	Upon Completion	Falkirk Council
An upgraded A9/A904 roundabout, Westfield Roundabout		WSP Deisgn Package	Project management records as per Section 6.3 Management and 6.4 M&E	Upon Completion	Falkirk Council
Improved pedestrian and cycle crossing facilities, by way of an iconic elevated bridge structure		WSP Deisgn Package	Project management records as per Section 6.3 Management and 6.4 M&E	Upon Completion	Falkirk Council
	Outcomes
New Housing	271 new homes	Gateway Development Agreement	Project management records as per Section 6.3 Management and 6.4 M&E	Quarterly	Falkirk Council
New Retail & Leisure Space	17,822 sqm of new retail & leisure	Gateway Development Agreement	Project management records as per Section 6.3 Management and 6.4 M&E	Quarterly	Falkirk Council
Falkirk Gateway Annual Walking Trips	645,000	WSP Estimates	Project management records as per Section 6.3 Management and 6.4 M&E	Quarterly	Falkirk Council
Falkirk Gateway Annual Cycling Trips	35,500	WSP Estimates	Project management records as per Section 6.3 Management and 6.4 M&E	Quarterly	Falkirk Council
	Impacts
Job growth	Gateway evaluation reports	Falkirk LUF Bid Submission	Project management records as per Section 6.3 Management and 6.4 M&E	At Gateway Milestones	Falkirk Council
Direct land value uplift	Gateway evaluation reports	Falkirk LUF Bid Submission	Project management records as per Section 6.3 Management and 6.4 M&E	At Gateway Milestones	Falkirk Council
Wider land value uplift	Gateway evaluation reports	Falkirk LUF Bid Submission	Project management records as per Section 6.3 Management and 6.4 M&E	At Gateway Milestones	Falkirk Council
Health and well-being impacts	Gateway evaluation reports	Falkirk LUF Bid Submission	Project management records as per Section 6.3 Management and 6.4 M&E	At Gateway Milestones	Falkirk Council

## 'file:///J:/332010573%20Falkirk%20Council%20LUF/Working/Economic%20Impact%20Assessment/Cashflow/10573-m01%20Falkirk%20Cashflow%20(quarterly)%20210608.xlsm'#Capital_Cost_Summary
		0.36856848002358833

Site Clearance
Fencing
Road Restraint Systems
Drainage
Earthworks
Pavements
Kerbs, Footways & Paved Areas
Traffic Signs & Road Markings
Road Lighting Columns, Brackets & CCTV Masts
Electrical Work for Road Lighting & Traffic Signs
Motorways Communications & Technology
Piling & Embedded Retaining Walls
Structural Concrete
Steelwork for Structures
Protection of Steelwork against Corrosion
Waterproofing for Structures
Bridge Bearings
Bridge Expansion Joints & Sealing of Gaps
Brickwork, Blockwork & Stonework
Special Structures (Midthorn Culvert)
Accommodation Works & Works for Statutory Undertakers
Landscape & Ecology
Maintenance Painting of Steelwork
Preliminaries
Contractors Fee/Overheads and Profit
Inception / Planning Fee
Project / Design Team Fees (Estimate)
Project Management Team Fees (Estimate)
G.I. 2019
Risk [per @Risk Output Report P85]
Historic Design and Preperation Costs
Inflation

## 'file:///J:/332010573%20Falkirk%20Council%20LUF/Working/Economic%20Impact%20Assessment/Cashflow/10573-m01%20Falkirk%20Cashflow%20(quarterly)%20210608.xlsm'#Cost_Entry_&_Inflation_Adjust_
389809.38
101497.46
787741.55
1595976.81
3716998.63
4328391.66
1694127.49
583604.29
653206.04
669999.84
0
4251666.07
877093.9
4746596.3099999996
470628
259128.2
68000
0
0
150976.5
2092338.2
723678.02
0
4928255.21
2587333.98
1248418
1408072.92
1854256.02
520000
5736780
5822308.8200000077
1997116.7

					10282590.646666678				27750844.196666669				16230565.156666676

## 'file:///J:/332010573%20Falkirk%20Council%20LUF/Working/Economic%20Impact%20Assessment/Cashflow/10573-m01%20Falkirk%20Cashflow%20(quarterly)%20210608.xlsm'#Economic_Costs
1145614.9949110642
20239198.2434288

34673794.430642232

## 'file:///J:/332010573%20Falkirk%20Council%20LUF/Working/Economic%20Impact%20Assessment/m1v02/10573-m1v02%20Falkirk%20RVUM%20210609.xlsm'#Outputs
64200467.870107092
30647938.228869587
781305.94196831982
2282095.0593984798
1362778.2551852069

## 'file:///J:/332010573%20Falkirk%20Council%20LUF/Working/210610-IL-Walk+Bicycle%20TRICS%20veh%20trip%20gen%20(no%20links)-1.XLSX'#Annualisation
495000
150000

28500
7000