## Sheet1
Strategtic Flood Risk Assessment Appendix 1 - Local Flood Risk Management Plan (LFMP) Actions and Timescales

Local Plan District	Potentially Vulnerable Area Reference	Potentially Vulnerable Area (PVA) Name	Target Area within PVA	Local authority area	LFMP Action 1 & ID	LFMP Action 1 Indicative Delivery	LFMP Action 1 Delivery Lead	LFMP Action 2 & ID	LFM Action 2 Indicative Delivery	LFMP Action 2 Delivery Lead	LFMP Action 3 & ID	LFMP Action 3 Indicative Delivery	LFMP Action 3 Delivery Lead	LFMP Action 4 & ID	LFMP Action 4 Indicative Delivery	LFMP Action 4 Delivery Lead	LFM Action 5 & ID	LFM Action 5 Indicative Delivery	LFM Action 5 Delivery Lead	LFM Action 6 & ID	LFM Action 6 Indicative Delivery	LFM Action 6 Delivery Lead
Forth Estuary Local Plan District	02/10/08	Airth	Airth (185)	Falkirk	Prepare a climate change adaptation plan to understand the likely impacts of climate change (ID 18501)	Before 2028	Falkirk Council	Undertake a review of coastal flooding modelling in this target area (ID 18503)	2023-2026	SEPA	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable
Forth Estuary Local Plan District	02/10/10	Falkirk and Grangemouth	Bonnybridge (201)	Falkirk	Prepare a surface water management plan for Bonnybridge (ID 20101)	Before 2028	Falkirk Council	N/A	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable
Forth Estuary Local Plan District	02/10/10	Falkirk and Grangemouth	Carron and Carronshore (211)	Falkirk	Folllowing notification in 2022, and subsequent confirmation, the Grangemouth Flood Protection Scheme will progress to the detailed design stage. A climate change adaptation plan will be developed to allow for the likely impacts of climate change to better considered (ID 21101)	2026-28	Falkirk Council	The detailed design of the Grangemouth Flood Protection Scheme is completed and the works have progressed to the procurement and construction phase. (ID 21102)	Construction phase estimated to take 10 years.	Falkirk Council	A modelling study is required to quanitfy the flood risk associated with the Chapel Burn. Some modelling of the lower reaches of the burn has been incorporated into the Grangemouth Flood Protection Scheme model (ID 21104)	Before 2028	Falkirk Council	Not applicable	Not applicable	Scottish Water	Prepare a surface water management plan for Carron and Carronshore (ID 21106)	Before 2028	Falkirk Council	Undertake a review of coastal flooding modelling in this target (ID 21109)	2023-2026	SEPA
Forth Estuary Local Plan District	02/10/10	Falkirk and Grangemouth	Denny and Dunipace (220)	Falkirk	Prepare a surface water management plan for Denny and Dunipace (ID 22002)	Before 2028	Falkirk Council	A flood protection study is to be progressed for this area to assess options to manage flood risk (ID 22001)	Before 2028	Falkirk Council	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable
Forth Estuary Local Plan District	02/10/10	Falkirk and Grangemouth	Falkirk (228)	Falkirk	Folllowing notification in 2022, and subsequent confirmation, the Grangemouth Flood Protection Scheme will progress to the detailed design stage. A climate change adaptation plan will be developed to allow for the likely impacts of climate change to better considered (ID 22801)	Cycle 2	Falkirk Council	The detailed design of the Grangemouth Flood Protection Scheme is completed and the works have progressed to the procurement and construction phase. (ID 22082)	Construction phase estimated to take 10 years.	Falkirk Council	Scottish Water to carry out an assessment of sewer flood risk within the highest priority sewer catchments in this target area (ID 22804).	2023-2025	Scottish Water	Not applicable	Not applicable	Falkirk Council	N/A	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable
Forth Estuary Local Plan District	02/10/10	Falkirk and Grangemouth	Grangemouth West (232)	Falkirk	Folllowing notification in 2022, and subsequent confirmation, the Grangemouth Flood Protection Scheme will progress to the detailed design stage. A climate change adaptation plan will be developed to allow for the likely impacts of climate change to better considered (ID 23201)	Second half of cycle 2	Falkirk Council	The detailed design of the Grangemouth Flood Protection Scheme is completed and the works have progressed to the procurement and construction phase. (ID 23202)	Construction phase estimated to take 10 years.	Falkirk Council	Scottish Water to carry out an assessment of sewer flood risk within the highest priority sewer catchments in this target area (ID 23204).	2023-2025	Scottish Water	Not applicable	Not applicable	Falkirk Council	Undertake a review of coastal flooding modelling in this target area (ID 23208)	2023-2026	SEPA	Not applicable	Not applicable	Not applicable
Forth Estuary Local Plan District	02/10/10	Falkirk and Grangemouth	Larbert and Stenhousemuir (243)	Falkirk	The selected preferred approach for managing flood risk is to be designed flollowing the completion of the flood study (ID 24301)	Cycle 2	Falkirk Council	Once confirmed and detailed design is underway, the Grangemouth Flood Protection Scheme will progress tto a rolling programme of procurement and construction (ID 24302)	Construction phase estimated to take 10 years.	Falkirk Council	A modelling study is required to quanitfy the flood risk associated with the Chapel Burn. Some modelling of the lower reaches of the burn has been incorporated into the Grangemouth Flood Protection Scheme model (ID 24304)	Before 2028	Falkirk Council	Not applicable	Not applicable	Scottish Water	Prepare a surface water management plan (ID: 24306)	Before 2028	Falkirk Council	Not applicable	Not applicable	Not applicable
Forth Estuary Local Plan District	'02/10/10	Falkirk and Grangemouth	Cumbernauld East (283)	Falkirk and North Lanarkshire	Scottish Water to carry out an assessment of sewer flood risk within the highest priority sewer catchments in this target area (ID 28601).	Cycle 2	Scottish Water	Priority areas will provide a baseline for the identification of next steps in managing water ponding or overwhlemed drainage systems (ID 28602)	Cycle 2	North Lanarkshire Council	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable
Forth Estuary Local Plan District	'02/10/10	Falkirk and Grangemouth	Polmont, Redding and Westquarter (308)	Falkirk	An understanding of flood risk and assoicated issues in the area is to be developed, which may include surveys and modelling. The flood study for the Westquarter Burn at Westquarter Village has been completed (ID 30801).	Completed in 2022	Falkirk Council	Scottish Water to carry out an assessment of sewer flood risk within the highest priority sewer catchments in this target area (ID30802).	2023-2025	Scottish Water	Prepare a surface water management plan for this target area including Polmonthill which identified as a hotspot(ID 30803)	Not applicable	Falkirk Council	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable
Forth Estuary Local Plan District	'02/10/11	Bo'ness	Bo'ness (200)	Falkirk	Scottish Water to carry out an assessment of sewer flood risk within the highest priority sewer catchments in this target area (ID 20001)	2025-2027	Scottish Water	The Bo'ness Surface Water Management Plan has been developed and has incorporated the outputs from the Bo'ness Intergrated Catchment Study and Scottish Water's assessment of sewer flood risk. Falkirk Councill will look into each hotspot with a review of preliminary design and funding for each if viable (ID 2002)	Before 2028	Falkirk Council	A climate change adaptation plan will be developed for the Bo'ness Flood Protection Scheme to allow for the likely impacts of climate chage to better understood (ID 2006)	Not applicable	Falkirk Council	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable
Forth Estuary Local Plan District	02/10/11	Bo'ness	Grangemouth East (262)	Falkirk	Folllowing notification in 2022, and subsequent confirmation, the Grangemouth Flood Protectionn Scheme will progress to the detailed design stage. A climate change adaptation plan will be developed to allow for the likely impacts of climate change to be better considered (ID 26201)	Second half of cycle 2	Falkirk Council	Once confirmed and detailed design is underway, the Grangemouth Flood Protection Scheme will progress to a rolling programme of procurement and construction (ID 26202)	Construction phase estimated to take 10 years.	Falkirk Council	Scottish Water to carry out an assessment of sewer flood risk within the highest priority sewer catchments in this target area (ID 2603).	Not applicable	Scottish Water	Not applicable	Not applicable	Falkirk Council	Undertake a review of coastal flooding modelling in this target area (ID 26207)	2023-2026	Not applicable	Not applicable	Not applicable	Not applicable
Forth Estuary Local Plan District	02/10/16	Slamannan	Slamannan (314)	Falkirk	An understanding of flood risk and assoicated issues in the area is to be developed, which may include surveys and modelling. A flood protection study is to be progressed for this area to assess options to manage flood risk (ID 31401)	Before 2028	Falkirk Council	Scottish Water to carry out an assessment of sewer flood risk within the highest priority sewer catchments in this target area (ID 31402).	2025-2027	Scottish Water	Priority areas will provide a baseline for the identification of next steps in managing water ponding or overwhlemed drainage systems (ID 31403). A surface water management plan to be prepared for Slamannan.	Not applicable	Falkirk Council	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable	Not applicable